SECTION 012500 - SUBSTITUTION PROCEDURES

GENERAL

SUMMARY

Section includes administrative and procedural requirements for substitutions.

Related Sections:

01 2501 - Substitution Request Form

01 3300 - Submittal Procedures:

01 6000 - Product Requirements:  For requirements for submitting comparable product submittals for products by listed manufacturers.

Divisions 02 through 49 Sections for specific requirements and limitations for substitutions.

DEFINITIONS

Substitutions:  Changes in products, materials, equipment, and methods of construction from those required by the Contract Documents and proposed by Contractor.

Substitutions for Cause:  Changes proposed by Contractor that are required due to changed Project conditions, such as unavailability of product, regulatory changes, or unavailability of required warranty terms.

Substitutions for Convenience:  Changes proposed by Contractor or Owner that are not required in order to meet other Project requirements but may offer advantage to Owner.

SUBMITTALS

Substitution Requests:  Prepare and submit each substitution request for consideration using the procedures listed in Section 01 3300 Submittal Procedures.  Identify product or fabrication or installation method to be replaced.  Include Specification Section number and title and Drawing numbers and titles.

Substitution Request Form:  Use copy of form provided in the Project Manual.

Documentation:  Show compliance with requirements for substitutions and the following, as applicable:

Statement indicating why specified product or fabrication or installation cannot be provided, if applicable.

Coordination information, including a list of changes or modifications needed to other parts of the Work and to construction performed by Owner and separate Contractors, that will be necessary to accommodate proposed substitution.

Detailed comparison of significant qualities of proposed substitution with those of the Work specified.  Include annotated copy of applicable specification section.  Significant qualities may include attributes such as performance, weight, size, durability, visual effect, sustainable design characteristics, warranties, and specific features and requirements indicated.  Indicate deviations, if any, from the Work specified.

Product Data, including drawings and descriptions of products and fabrication and installation procedures.

Samples, where applicable or requested.

Certificates and qualification data, where applicable or requested.

List of similar installations for completed projects with project names and addresses and names and addresses of architects and owners.

Material test reports from a qualified testing agency indicating and interpreting test results for compliance with requirements indicated.

Research reports evidencing compliance with building code in effect for Project, from ICC-ES.

Detailed comparison of Contractor's construction schedule using proposed substitution with products specified for the Work, including effect on the overall Contract Time.  If specified product or method of construction cannot be provided within the Contract Time, include letter from manufacturer, on manufacturer's letterhead, stating date of receipt of purchase order, lack of availability, or delays in delivery.

Cost information, including a proposal of change, if any, in the Contract Sum.

Contractor's certification that proposed substitution complies with requirements in the Contract Documents except as indicated in substitution request, is compatible with related materials, and is appropriate for applications indicated.

Contractor's waiver of rights to additional payment or time that may subsequently become necessary because of failure of proposed substitution to produce indicated results.

Architect's Action:  If necessary, Architect will request additional information or documentation for evaluation within seven days of receipt of a request for substitution.  Architect will notify Contractor of acceptance or rejection of proposed substitution within 10 days of receipt of request, or seven days of receipt of additional information or documentation, whichever is later.

Forms of Acceptance:  Change Order, Construction Change Directive, or Architect's Supplemental Instructions for minor changes in the Work.

Use product specified if Architect does not issue a decision on use of a proposed substitution within time allocated.

QUALITY ASSURANCE

Compatibility of Substitutions:  Investigate and document compatibility of proposed substitution with related products and materials.  Engage qualified testing agency to perform compatibility tests recommended by manufacturers.

PROCEDURES

Coordination:  Modify or adjust affected work as necessary to integrate work of the approved substitutions.

PRODUCTS

SUBSTITUTIONS

Substitutions for Cause:  Submit requests for substitution immediately upon discovery of need for change, but not later than 15 days prior to time required for preparation and review of related submittals.

Conditions:  Architect will consider Contractor's request for substitution when the following conditions are satisfied.  If the following conditions are not satisfied, Architect will return requests without action, except to record noncompliance with these requirements:

Requested substitution is consistent with the Contract Documents and will produce indicated results.

Substitution request is fully documented and properly submitted.

Requested substitution will not adversely affect Contractor's construction schedule.

Requested substitution has received necessary approvals of authorities having jurisdiction.

Requested substitution is compatible with other portions of the Work.

Requested substitution has been coordinated with other portions of the Work.

Requested substitution provides specified warranty.

If requested substitution involves more than one contractor, requested substitution has been coordinated with other portions of the Work, is uniform and consistent, is compatible with other products, and is acceptable to all contractors involved.

Substitutions for Convenience:  Architect will consider requests for substitution if received within 60 days after commencement of the Work.  Requests received after that time may be considered or rejected at discretion of Architect.

Conditions:  Architect will consider Contractor's request for substitution when the following conditions are satisfied.  If the following conditions are not satisfied, Architect will return requests without action, except to record noncompliance with these requirements:

Requested substitution offers Owner a substantial advantage in cost, time, energy conservation, or other considerations, after deducting additional responsibilities Owner must assume.  Owner's additional responsibilities may include compensation to Architect for redesign and evaluation services, increased cost of other construction by Owner, and similar considerations.

Requested substitution does not require extensive revisions to the Contract Documents.

Requested substitution is consistent with the Contract Documents and will produce indicated results.

Substitution request is fully documented and properly submitted.

Requested substitution will not adversely affect Contractor's construction schedule.

Requested substitution has received necessary approvals of authorities having jurisdiction.

Requested substitution is compatible with other portions of the Work.

Requested substitution has been coordinated with other portions of the Work.

Requested substitution provides specified warranty.

If requested substitution involves more than one contractor, requested substitution has been coordinated with other portions of the Work, is uniform and consistent, is compatible with other products, and is acceptable to all contractors involved.

EXECUTION (Not Used)

END OF SECTION